## Financial Report
FINANCIAL EXTRACT 12/22/2025
Fnd | Fc | Job | Sub Objt Description | Life Rev Budget | 2025Encumbrances / Requisitions | Life Actual | Life Available | Job Mgr
661 | 41 | 000000 | Admin & Operations (CIP) | 4122.5 | 0 | 567 | 3555.5 | ISD
661 | 51 | 000000 | Building & Land Acquisition (CIP) | 1426450 | 790650 | 635800 | 0 | ISD
661 | 71 | 000000 | Basic | 456372.67 | 0 | 456372.67 | 0 | ISD
661 | 71 | 000000 | Basic | 16128.33 | 0 | 16128.33 | 0 | ISD
661 | 81 | 000000 | Admin & Operations (CIP) | 0 | 0 | 0 | 0 | ISD
661 | 81 | 000000 | Admin & Operations (CIP) | 3988393 | 0 | 1478355.74 | 2510037.26 | ISD
661 | 81 | 000000 | Admin & Operations (CIP) | 9700 | 0 | 15.39 | 9684.61 | ISD
661 | 81 | 021111 | Overtime (CIP) | 7422 | 0 | 6843.56 | 578.44 | OR
661 | 81 | 042101 | Overtime (CIP) | 19334 | 0 | 0 | 19334 | OR
661 | 81 | 044201 | Overtime (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 044202 | Overtime (CIP) | 49907 | 0 | 0 | 49907 | OR
661 | 81 | 045101 | Overtime (CIP) | 22944 | 0 | 3337.94 | 19606.06 | OR
661 | 81 | 048101 | Overtime (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 048102 | Overtime (CIP) | 61253.81 | 0 | 0 | 61253.81 | OR
661 | 81 | 049101 | Overtime (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 050102 | Overtime (CIP) | 44196 | 0 | 0 | 44196 | OR
661 | 81 | 051301 | Overtime (CIP) | 31374 | 0 | 25176.51 | 6197.49 | OR
661 | 81 | 052201 | Overtime (CIP) | 27262 | 0 | 0 | 27262 | OR
661 | 81 | 053301 | Overtime (CIP) | 25064 | 0 | 0 | 25064 | OR
661 | 81 | 054301 | Overtime (CIP) | 17.66 | 0 | 17.66 | 0 | OR
661 | 81 | 055202 | Overtime (CIP) | 15000 | 0 | 0 | 15000 | OR
661 | 81 | 056301 | Overtime (CIP) | 19324 | 0 | 3366 | 15958 | OR
661 | 81 | 057201 | Overtime (CIP) | 32079 | 0 | 1395 | 30684 | OR
661 | 81 | 058101 | Overtime (CIP) | 24940 | 0 | 9496.16 | 15443.84 | OR
661 | 81 | 059101 | Overtime (CIP) | 18801 | 0 | 8470.99 | 10330.01 | OR
661 | 81 | 060101 | Overtime (CIP) | 26885 | 0 | 11361.28 | 15523.72 | OR
661 | 81 | 061201 | Overtime (CIP) | 27465 | 0 | 856.57 | 26608.43 | OR
661 | 81 | 070301 | Overtime (CIP) | 16023 | 0 | 0 | 16023 | OR
661 | 81 | 081204 | Overtime (CIP) | 11200 | 0 | 0 | 11200 | OR
661 | 81 | 125131 | Overtime (CIP) | 18732 | 0 | 0 | 18732 | OR
661 | 81 | 147101 | Overtime (CIP) | 139.37 | 0 | 139.37 | 0 | OR
661 | 81 | 160131 | Overtime (CIP) | 18732 | 0 | 0 | 18732 | OR
661 | 81 | 184131 | Overtime (CIP) | 18732 | 0 | 0 | 18732 | OR
661 | 81 | 194101 | Overtime (CIP) | 8832 | 0 | 641.57 | 8190.43 | OR
661 | 81 | 256131 | Overtime (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 000000 | Admin & Operations (CIP) | 1875 | 0 | 320.63 | 1554.37 | ISD
661 | 81 | 000000 | Admin & Operations (CIP) | 165000 | 0 | 19677.77 | 145322.23 | ISD
661 | 81 | 000000 | Admin & Operations (CIP) | 61000 | 0 | 18114.93 | 42885.07 | ISD
661 | 81 | 000000 | Admin & Operations (CIP) | 13000 | 0 | 5536.72 | 7463.28 | ISD
661 | 81 | 000000 | Admin & Operations (CIP) | 78000 | 0 | 21222.01 | 56777.99 | ISD
661 | 81 | 021111 | Overtime (CIP) | 800 | 0 | 98.86 | 701.14 | OR
661 | 81 | 045101 | Overtime (CIP) | 1500 | 0 | 48.92 | 1451.08 | OR
661 | 81 | 051301 | Overtime (CIP) | 1000 | 0 | 255.59 | 744.41 | OR
661 | 81 | 054301 | Overtime (CIP) | 0.26 | 0 | 0.26 | 0 | OR
661 | 81 | 055202 | Overtime (CIP) | 1000 | 0 | 0 | 1000 | OR
661 | 81 | 056301 | Overtime (CIP) | 1000 | 0 | 52.75 | 947.25 | OR
661 | 81 | 057201 | Overtime (CIP) | 1000 | 0 | 19.6 | 980.4 | OR
661 | 81 | 058101 | Overtime (CIP) | 500 | 0 | 136.28 | 363.72 | OR
661 | 81 | 059101 | Overtime (CIP) | 1000 | 0 | 124.63 | 875.37 | OR
661 | 81 | 060101 | Overtime (CIP) | 1500 | 0 | 164.8 | 1335.2 | OR
661 | 81 | 061201 | Overtime (CIP) | 300 | 0 | 13.23 | 286.77 | OR
661 | 81 | 061201 | Overtime (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 125131 | Overtime (CIP) | 1500 | 0 | 0 | 1500 | OR
661 | 81 | 147101 | Overtime (CIP) | 2.02 | 0 | 2.02 | 0 | OR
661 | 81 | 160131 | Overtime (CIP) | 1500 | 0 | 0 | 1500 | OR
661 | 81 | 184131 | Overtime (CIP) | 1500 | 0 | 0 | 1500 | OR
661 | 81 | 194101 | Overtime (CIP) | 1000 | 0 | 9.25 | 990.75 | OR
661 | 81 | 000000 | Admin & Operations (CIP) | 160000 | 0 | 38199.84 | 121800.16 | ISD
661 | 81 | 021111 | Overtime (CIP) | 400 | 0 | 155.2 | 244.8 | OR
661 | 81 | 045101 | Overtime (CIP) | 1000 | 0 | 1.05 | 998.95 | OR
661 | 81 | 051301 | Overtime (CIP) | 2000 | 0 | 383.19 | 1616.81 | OR
661 | 81 | 055202 | Overtime (CIP) | 1538 | 0 | 0 | 1538 | OR
661 | 81 | 056301 | Overtime (CIP) | 2000 | 0 | 2.16 | 1997.84 | OR
661 | 81 | 057201 | Overtime (CIP) | 2000 | 0 | 26.51 | 1973.49 | OR
661 | 81 | 058101 | Overtime (CIP) | 3100 | 0 | 396.11 | 2703.89 | OR
661 | 81 | 059101 | Overtime (CIP) | 1000 | 0 | 6.98 | 993.02 | OR
661 | 81 | 060101 | Overtime (CIP) | 1000 | 0 | 194.81 | 805.19 | OR
661 | 81 | 125131 | Overtime (CIP) | 1000 | 0 | 0 | 1000 | OR
661 | 81 | 147101 | Overtime (CIP) | 0.33 | 0 | 0.33 | 0 | OR
661 | 81 | 160131 | Overtime (CIP) | 1000 | 0 | 0 | 1000 | OR
661 | 81 | 184131 | Overtime (CIP) | 1000 | 0 | 0 | 1000 | OR
661 | 81 | 194101 | Overtime (CIP) | 1000 | 0 | 0.24 | 999.76 | OR
661 | 81 | 000000 | Admin & Operations (CIP) | 51000 | 0 | 11474.49 | 39525.51 | ISD
661 | 81 | 021111 | Overtime (CIP) | 800 | 0 | 52.92 | 747.08 | OR
661 | 81 | 045101 | Overtime (CIP) | 1750 | 0 | 25.19 | 1724.81 | OR
661 | 81 | 051301 | Overtime (CIP) | 1000 | 0 | 126.11 | 873.89 | OR
661 | 81 | 054301 | Overtime (CIP) | 0.27 | 0 | 0.27 | 0 | OR
661 | 81 | 055202 | Overtime (CIP) | 1000 | 0 | 0 | 1000 | OR
661 | 81 | 056301 | Overtime (CIP) | 1000 | 0 | 25.69 | 974.31 | OR
661 | 81 | 057201 | Overtime (CIP) | 1000 | 0 | 10.45 | 989.55 | OR
661 | 81 | 058101 | Overtime (CIP) | 1500 | 0 | 70.91 | 1429.09 | OR
661 | 81 | 059101 | Overtime (CIP) | 1000 | 0 | 64.04 | 935.96 | OR
661 | 81 | 060101 | Overtime (CIP) | 1750 | 0 | 85.51 | 1664.49 | OR
661 | 81 | 125131 | Overtime (CIP) | 1750 | 0 | 0 | 1750 | OR
661 | 81 | 147101 | Overtime (CIP) | 1.05 | 0 | 1.05 | 0 | OR
661 | 81 | 160131 | Overtime (CIP) | 1750 | 0 | 0 | 1750 | OR
661 | 81 | 184131 | Overtime (CIP) | 1750 | 0 | 0 | 1750 | OR
661 | 81 | 194101 | Overtime (CIP) | 1000 | 0 | 4.82 | 995.18 | OR
661 | 81 | 000000 | Admin & Operations (CIP) | 20000 | 0 | 3240.66 | 16759.34 | ISD
661 | 81 | 021111 | Overtime (CIP) | 300 | 0 | 11.98 | 288.02 | OR
661 | 81 | 045101 | Overtime (CIP) | 1000 | 0 | 6.5 | 993.5 | OR
661 | 81 | 051301 | Overtime (CIP) | 1000 | 0 | 17.8 | 982.2 | OR
661 | 81 | 055202 | Overtime (CIP) | 1000 | 0 | 0 | 1000 | OR
661 | 81 | 056301 | Overtime (CIP) | 1000 | 0 | 2.75 | 997.25 | OR
661 | 81 | 057201 | Overtime (CIP) | 1000 | 0 | 3.48 | 996.52 | OR
661 | 81 | 058101 | Overtime (CIP) | 1250 | 0 | 18.8 | 1231.2 | OR
661 | 81 | 059101 | Overtime (CIP) | 1000 | 0 | 16.42 | 983.58 | OR
661 | 81 | 060101 | Overtime (CIP) | 1000 | 0 | 24.99 | 975.01 | OR
661 | 81 | 125131 | Overtime (CIP) | 1000 | 0 | 0 | 1000 | OR
661 | 81 | 147101 | Overtime (CIP) | 0.35 | 0 | 0.35 | 0 | OR
661 | 81 | 160131 | Overtime (CIP) | 1000 | 0 | 0 | 1000 | OR
661 | 81 | 184131 | Overtime (CIP) | 1000 | 0 | 0 | 1000 | OR
661 | 81 | 194101 | Overtime (CIP) | 1000 | 0 | 1.49 | 998.51 | OR
661 | 81 | 000000 | Admin & Operations (CIP) | 187000 | 0 | 38900.96 | 148099.04 | ISD
661 | 81 | 021111 | Overtime (CIP) | 400 | 0 | 287.48 | 112.52 | OR
661 | 81 | 045101 | Overtime (CIP) | 1750 | 0 | 37.43 | 1712.57 | OR
661 | 81 | 051301 | Overtime (CIP) | 2000 | 0 | 640.33 | 1359.67 | OR
661 | 81 | 055202 | Overtime (CIP) | 1530 | 0 | 0 | 1530 | OR
661 | 81 | 056301 | Overtime (CIP) | 2000 | 0 | 86.35 | 1913.65 | OR
661 | 81 | 057201 | Overtime (CIP) | 2000 | 0 | 37.93 | 1962.07 | OR
661 | 81 | 058101 | Overtime (CIP) | 2100 | 0 | 204.13 | 1895.87 | OR
661 | 81 | 059101 | Overtime (CIP) | 1000 | 0 | 318.54 | 681.46 | OR
661 | 81 | 060101 | Overtime (CIP) | 1750 | 0 | 199.17 | 1550.83 | OR
661 | 81 | 061201 | Overtime (CIP) | 300 | 0 | 23.97 | 276.03 | OR
661 | 81 | 125131 | Overtime (CIP) | 1750 | 0 | 0 | 1750 | OR
661 | 81 | 147101 | Overtime (CIP) | 3.7 | 0 | 3.7 | 0 | OR
661 | 81 | 160131 | Overtime (CIP) | 1750 | 0 | 0 | 1750 | OR
661 | 81 | 184131 | Overtime (CIP) | 1750 | 0 | 0 | 1750 | OR
661 | 81 | 194101 | Overtime (CIP) | 1000 | 0 | 5.13 | 994.87 | OR
661 | 81 | 000000 | Admin & Operations (CIP) | 5000 | 0 | 1919.37 | 3080.63 | ISD
661 | 81 | 021111 | Overtime (CIP) | 300 | 0 | 8.63 | 291.37 | OR
661 | 81 | 045101 | Overtime (CIP) | 1000 | 0 | 4.68 | 995.32 | OR
661 | 81 | 051301 | Overtime (CIP) | 1000 | 0 | 12.21 | 987.79 | OR
661 | 81 | 055202 | Overtime (CIP) | 1000 | 0 | 0 | 1000 | OR
661 | 81 | 056301 | Overtime (CIP) | 1000 | 0 | 1.98 | 998.02 | OR
661 | 81 | 057201 | Overtime (CIP) | 1000 | 0 | 2.52 | 997.48 | OR
661 | 81 | 058101 | Overtime (CIP) | 1250 | 0 | 13.54 | 1236.46 | OR
661 | 81 | 059101 | Overtime (CIP) | 1000 | 0 | 10.78 | 989.22 | OR
661 | 81 | 060101 | Overtime (CIP) | 1000 | 0 | 17.74 | 982.26 | OR
661 | 81 | 147101 | Overtime (CIP) | 0.25 | 0 | 0.25 | 0 | OR
661 | 81 | 194101 | Overtime (CIP) | 300 | 0 | 1.08 | 298.92 | OR
661 | 81 | 000000 | Admin & Operations (CIP) | 15877.5 | 0 | 15877.5 | 0 | ISD
661 | 81 | 000000 | Admin & Operations (CIP) | 10000 | 901.7 | 1898.25 | 7200.05 | ISD
661 | 81 | 000000 | Building & Land Acquisition (CIP) | 145200 | 0 | 128152.38 | 17047.62 | ISD
661 | 81 | 000000 | Admin & Operations (CIP) | 50000 | 0 | 8254.72 | 41745.28 | ISD
661 | 81 | 000000 | Admin & Operations (CIP) | 2242200 | 0 | 2242200 | 0 | ISD
661 | 81 | 000000 | Admin & Operations (CIP) | 64000 | 43657 | 18002.06 | 2340.94 | ISD
661 | 81 | 000000 | Moving (CIP) | 40000 | 0 | 8815 | 31185 | ISD
661 | 81 | 042101 | Furniture, Fixture, & Equipment (CIP) | 1462110 | 0 | 0 | 1462110 | OR
661 | 81 | 081204 | Furniture, Fixture, & Equipment (CIP) | 847000 | 0 | 0 | 847000 | OR
661 | 81 | 256131 | Furniture, Fixture, & Equipment (CIP) | 2935340.03 | 0 | 2161277.85 | 774062.18 | OR
661 | 81 | 000000 | Admin & Operations (CIP) | 100000 | 43.41 | 19880.43 | 80076.16 | ISD
661 | 81 | 000000 | Moving (CIP) | 20000 | 0 | 6257.3 | 13742.7 | ISD
661 | 81 | 000000 | Mileage Reimbursemen | 5000 | 0 | 8.4 | 4991.6 | ISD
661 | 81 | 000000 | Admin & Operations (CIP) | 61000 | 568.01 | 10936.83 | 49495.16 | ISD
661 | 81 | 000000 | Advertisements/Bids (CIP) | 55000 | 1209 | 3034 | 50757 | ISD
661 | 81 | 000000 | Admin & Operations (CIP) | 182200 | 0 | 66895.8 | 115304.2 | ISD
661 | 81 | 000000 | Food Purchase | 10000 | 0 | 6785.72 | 3214.28 | ISD
661 | 81 | 000000 | Admin & Operations (CIP) | 25000 | 0 | 6059.99 | 18940.01 | ISD
661 | 81 | 999399 | Building & Land Acquisition (CIP) | 9081885 | 110586.45 | 3057691.12 | 5913607.43 | OR
661 | 81 | 045831 | Basic | 82000 | 35322.56 | 0 | 46677.44 | ISD
661 | 81 | 021821 | Operations Management | 138873 | 0 | 138872.5 | 0.5 | ISD
661 | 81 | 061821 | Operations Management | 61389 | 61389 | 0 | 0 | ISD
661 | 81 | 081821 | Operations Management | 80333 | 0 | 80333 | 0 | ISD
661 | 81 | 021111 | A/E Services (CIP) | 59180 | 4356 | 54824 | 0 | OR
661 | 81 | 042101 | A/E Services (CIP) | 30209 | 0 | 0 | 30209 | OR
661 | 81 | 044201 | A/E Services (CIP) | 76860 | 0 | 76860 | 0 | OR
661 | 81 | 044202 | A/E Services (CIP) | 34236 | 0 | 0 | 34236 | OR
661 | 81 | 045101 | A/E Services (CIP) | 59825 | 0 | 59825 | 0 | OR
661 | 81 | 045102 | A/E Services (CIP) | 14365 | 0 | 14364.28 | 0.72 | OR
661 | 81 | 048101 | A/E Services (CIP) | 29856 | 0 | 29856 | 0 | OR
661 | 81 | 048102 | A/E Services (CIP) | 16629 | 0 | 0 | 16629 | OR
661 | 81 | 049101 | A/E Services (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 050101 | A/E Services (CIP) | 85000 | 0 | 85000 | 0 | OR
661 | 81 | 050102 | A/E Services (CIP) | 147321 | 0 | 0 | 147321 | OR
661 | 81 | 051301 | A/E Services (CIP) | 45896 | 0 | 25382.6 | 20513.4 | OR
661 | 81 | 052201 | A/E Services (CIP) | 42598 | 10270 | 0 | 32328 | OR
661 | 81 | 053301 | A/E Services (CIP) | 39162 | 0 | 0 | 39162 | OR
661 | 81 | 054301 | A/E Services (CIP) | 58700 | 0 | 58700 | 0 | OR
661 | 81 | 055202 | A/E Services (CIP) | 787741.06 | 59490 | 18245 | 710006.06 | OR
661 | 81 | 056301 | A/E Services (CIP) | 42694 | 0 | 4195.65 | 38498.35 | OR
661 | 81 | 057201 | A/E Services (CIP) | 181980 | 0 | 0 | 181980 | OR
661 | 81 | 058101 | A/E Services (CIP) | 172585 | 18336.8 | 154248.2 | 0 | OR
661 | 81 | 059101 | A/E Services (CIP) | 38752 | 0 | 22000 | 16752 | OR
661 | 81 | 060101 | A/E Services (CIP) | 54508 | 0 | 22100 | 32408 | OR
661 | 81 | 061201 | A/E Services (CIP) | 43852 | 0 | 0 | 43852 | OR
661 | 81 | 070301 | A/E Services (CIP) | 25036 | 0 | 0 | 25036 | OR
661 | 81 | 081204 | A/E Services (CIP) | 17500 | 0 | 0 | 17500 | OR
661 | 81 | 125131 | A/E Services (CIP) | 89750 | 0 | 89750 | 0 | OR
661 | 81 | 147101 | A/E Services (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 160131 | A/E Services (CIP) | 60500 | 0.01 | 36300 | 24199.99 | OR
661 | 81 | 184131 | A/E Services (CIP) | 40205 | 12600 | 23100 | 4505 | OR
661 | 81 | 194101 | A/E Services (CIP) | 22082 | 0 | 0 | 22082 | OR
661 | 81 | 021111 | RAS Accessibility (CIP) | 5000 | 3500 | 0 | 1500 | OR
661 | 81 | 042101 | RAS Accessibility (CIP) | 5000 | 2191 | 1309 | 1500 | OR
661 | 81 | 044201 | RAS Accessibility (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 044202 | RAS Accessibility (CIP) | 3500 | 0 | 0 | 3500 | OR
661 | 81 | 045101 | RAS Accessibility (CIP) | 5000 | 1355 | 2145 | 1500 | OR
661 | 81 | 045102 | RAS Accessibility (CIP) | 3500 | 2713.34 | 786.66 | 0 | OR
661 | 81 | 048101 | RAS Accessibility (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 048102 | RAS Accessibility (CIP) | 3000 | 0 | 0 | 3000 | OR
661 | 81 | 049101 | RAS Accessibility (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 050102 | RAS Accessibility (CIP) | 7366 | 3500 | 0 | 3866 | OR
661 | 81 | 051301 | RAS Accessibility (CIP) | 5000 | 1301.07 | 2198.93 | 1500 | OR
661 | 81 | 052201 | RAS Accessibility (CIP) | 5000 | 3500 | 0 | 1500 | OR
661 | 81 | 053301 | RAS Accessibility (CIP) | 5000 | 947.22 | 2552.78 | 1500 | OR
661 | 81 | 054301 | RAS Accessibility (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 055201 | RAS Accessibility (CIP) | 3500 | 0 | 0 | 3500 | OR
661 | 81 | 055202 | RAS Accessibility (CIP) | 10000 | 3500 | 0 | 6500 | OR
661 | 81 | 056301 | RAS Accessibility (CIP) | 5000 | 1679.44 | 1820.56 | 1500 | OR
661 | 81 | 057201 | RAS Accessibility (CIP) | 5000 | 2145 | 2855 | 0 | OR
661 | 81 | 058101 | RAS Accessibility (CIP) | 5000 | 0 | 0 | 5000 | OR
661 | 81 | 059101 | RAS Accessibility (CIP) | 5000 | 745.02 | 2754.98 | 1500 | OR
661 | 81 | 060101 | RAS Accessibility (CIP) | 5000 | 3500 | 0 | 1500 | OR
661 | 81 | 061201 | RAS Accessibility (CIP) | 5000 | 727.4 | 2772.6 | 1500 | OR
661 | 81 | 070301 | RAS Accessibility (CIP) | 5000 | 2696.35 | 803.65 | 1500 | OR
661 | 81 | 081204 | RAS Accessibility (CIP) | 5000 | 3500 | 0 | 1500 | OR
661 | 81 | 125131 | RAS Accessibility (CIP) | 5000 | 3500 | 0 | 1500 | OR
661 | 81 | 147101 | RAS Accessibility (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 160131 | RAS Accessibility (CIP) | 5000 | 166.25 | 3333.75 | 1500 | OR
661 | 81 | 184131 | RAS Accessibility (CIP) | 5000 | 3500 | 0 | 1500 | OR
661 | 81 | 194101 | RAS Accessibility (CIP) | 5000 | 3500 | 0 | 1500 | OR
661 | 81 | 256131 | RAS Accessibility (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 021111 | Abatement (CIP) | 704551 | 20445 | 684105.02 | 0.98 | OR
661 | 81 | 042101 | Abatement (CIP) | 339341 | 0 | 0 | 339341 | OR
661 | 81 | 044201 | Abatement (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 044202 | Abatement (CIP) | 1153613 | 0 | 0 | 1153613 | OR
661 | 81 | 045101 | Abatement (CIP) | 661567 | 402661.04 | 258904.97 | 0.99 | OR
661 | 81 | 048101 | Abatement (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 048102 | Abatement (CIP) | 796087 | 0 | 0 | 796087 | OR
661 | 81 | 049101 | Abatement (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 050102 | Abatement (CIP) | 1104908 | 0 | 0 | 1104908 | OR
661 | 81 | 051301 | Abatement (CIP) | 464921 | 231189.85 | 233730.39 | 0.76 | OR
661 | 81 | 052201 | Abatement (CIP) | 926919 | 926918.06 | 0 | 0.94 | OR
661 | 81 | 053301 | Abatement (CIP) | 463573 | 443258.56 | 0 | 20314.44 | OR
661 | 81 | 054301 | Abatement (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 055201 | Abatement (CIP) | 12767 | 0 | 12767 | 0 | OR
661 | 81 | 055202 | Abatement (CIP) | 519569 | 0 | 0 | 519569 | OR
661 | 81 | 056301 | Abatement (CIP) | 784578 | 416531.1 | 368045.92 | 0.98 | OR
661 | 81 | 057201 | Abatement (CIP) | 1458115 | 627092.89 | 831021.24 | 0.87 | OR
661 | 81 | 058101 | Abatement (CIP) | 486987 | 76077.98 | 148203.62 | 262705.4 | OR
661 | 81 | 059101 | Abatement (CIP) | 659842 | 546934.4 | 112907.42 | 0.18 | OR
661 | 81 | 060101 | Abatement (CIP) | 1065226 | 137630 | 927595.48 | 0.52 | OR
661 | 81 | 061201 | Abatement (CIP) | 1110693 | 716363.29 | 394329.13 | 0.58 | OR
661 | 81 | 070301 | Abatement (CIP) | 198310 | 0 | 0 | 198310 | OR
661 | 81 | 125131 | Abatement (CIP) | 1799662 | 188673.5 | 1447383.66 | 163604.84 | OR
661 | 81 | 160131 | Abatement (CIP) | 380631 | 325481.5 | 55148.78 | 0.72 | OR
661 | 81 | 194101 | Abatement (CIP) | 315196 | 186530 | 33210.12 | 95455.88 | OR
661 | 81 | 021111 | Design Services (CIP) | 1053278 | 124744.96 | 928532.19 | 0.85 | OR
661 | 81 | 042101 | Design Services (CIP) | 2003354 | 508760 | 597240 | 897354 | OR
661 | 81 | 044201 | Design Services (CIP) | 346970.64 | 0 | 346970.08 | 0.56 | OR
661 | 81 | 044202 | Design Services (CIP) | 4423027.71 | 3823750 | 546250 | 53027.71 | OR
661 | 81 | 045101 | Design Services (CIP) | 3272822 | 705946.99 | 2488383.41 | 78491.6 | OR
661 | 81 | 045102 | Design Services (CIP) | 428907 | 4401.15 | 334148.85 | 90357 | OR
661 | 81 | 048101 | Design Services (CIP) | 384263.82 | 0 | 384263.07 | 0.75 | OR
661 | 81 | 048102 | Design Services (CIP) | 4370000.31 | 4370000 | 0 | 0.31 | OR
661 | 81 | 049101 | Design Services (CIP) | 111922.65 | 0 | 111922.24 | 0.41 | OR
661 | 81 | 050101 | Design Services (CIP) | 563019.82 | 0 | 563019.82 | 0 | OR
661 | 81 | 050102 | Design Services (CIP) | 5588574 | 2304598.2 | 3283975.8 | 0 | OR
661 | 81 | 051301 | Design Services (CIP) | 3076007 | 670569.51 | 2405437.43 | 0.06 | OR
661 | 81 | 052201 | Design Services (CIP) | 2817196 | 986018.25 | 1831176.79 | 0.96 | OR
661 | 81 | 053301 | Design Services (CIP) | 2581697 | 1026894.45 | 1477726.18 | 77076.37 | OR
661 | 81 | 054301 | Design Services (CIP) | 597927.87 | 0 | 597927.39 | 0.48 | OR
661 | 81 | 055201 | Design Services (CIP) | 1137280.44 | 0 | 987073.59 | 150206.85 | OR
661 | 81 | 055202 | Design Services (CIP) | 2124945 | 864264.26 | 936286.28 | 324394.46 | OR
661 | 81 | 056301 | Design Services (CIP) | 2814523 | 713203.33 | 2094683.81 | 6635.86 | OR
661 | 81 | 057201 | Design Services (CIP) | 4336781 | 1196996.34 | 3139783.3 | 1.36 | OR
661 | 81 | 058101 | Design Services (CIP) | 3669667 | 389482.79 | 3250543.43 | 29640.78 | OR
661 | 81 | 059101 | Design Services (CIP) | 2622087 | 382824.64 | 2239262.05 | 0.31 | OR
661 | 81 | 060101 | Design Services (CIP) | 3621384 | 528721.93 | 3092661.16 | 0.91 | OR
661 | 81 | 061201 | Design Services (CIP) | 2890871 | 720096.09 | 1996818.7 | 173956.21 | OR
661 | 81 | 069101 | Design Services (CIP) | 319567.13 | 0 | 319567.13 | 0 | OR
661 | 81 | 070301 | Design Services (CIP) | 1650452 | 377671.17 | 937359.24 | 335421.59 | OR
661 | 81 | 081204 | Design Services (CIP) | 1183875 | 963602.5 | 170047.5 | 50225 | OR
661 | 81 | 125131 | Design Services (CIP) | 3152243 | 1126885 | 1992362.1 | 32995.9 | OR
661 | 81 | 147101 | Design Services (CIP) | 426313.43 | 0 | 263327.64 | 162985.79 | OR
661 | 81 | 160131 | Design Services (CIP) | 2719900 | 999398.26 | 1636835.84 | 83665.9 | OR
661 | 81 | 184131 | Design Services (CIP) | 4719900 | 2269880.25 | 882731.23 | 1567288.52 | OR
661 | 81 | 194101 | Design Services (CIP) | 1455727 | 332595.96 | 838515.37 | 284615.67 | OR
661 | 81 | 021111 | Construction Cost Budget (CIP) | 12994660 | 2666689.75 | 10075740.75 | 252229.5 | OR
661 | 81 | 042101 | Construction Cost Budget (CIP) | 26768695 | 20000 | 0 | 26748695 | OR
661 | 81 | 044201 | Construction Cost Budget (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 044202 | Construction Cost Budget (CIP) | 69427811 | 0 | 0 | 69427811 | OR
661 | 81 | 045101 | Construction Cost Budget (CIP) | 42859980 | 24091076.76 | 18768902.84 | 0.4 | OR
661 | 81 | 048101 | Construction Cost Budget (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 048102 | Construction Cost Budget (CIP) | 84407762 | 0 | 0 | 84407762 | OR
661 | 81 | 049101 | Construction Cost Budget (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 050102 | Construction Cost Budget (CIP) | 51064186 | 0 | 0 | 51064186 | OR
661 | 81 | 051301 | Construction Cost Budget (CIP) | 40309759 | 20574472.01 | 19634768.99 | 100518 | OR
661 | 81 | 052201 | Construction Cost Budget (CIP) | 37518787 | 35919138 | 910941 | 688708 | OR
661 | 81 | 053301 | Construction Cost Budget (CIP) | 35226828 | 0 | 0 | 35226828 | OR
661 | 81 | 054301 | Construction Cost Budget (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 055201 | Construction Cost Budget (CIP) | 1750 | 0 | 1750 | 0 | OR
661 | 81 | 055202 | Construction Cost Budget (CIP) | 24246574 | 20000 | 0 | 24226574 | OR
661 | 81 | 056301 | Construction Cost Budget (CIP) | 37398673 | 22013499.56 | 15288356.44 | 96817 | OR
661 | 81 | 057201 | Construction Cost Budget (CIP) | 54802739 | 39587551.6 | 14577038.4 | 638149 | OR
661 | 81 | 058101 | Construction Cost Budget (CIP) | 46892957 | 8683097.89 | 38209859.11 | 0 | OR
661 | 81 | 059101 | Construction Cost Budget (CIP) | 34674492 | 10123948.15 | 24226694.85 | 323849 | OR
661 | 81 | 060101 | Construction Cost Budget (CIP) | 47755399 | 13118383.84 | 34254957.16 | 382058 | OR
661 | 81 | 061201 | Construction Cost Budget (CIP) | 36196670 | 16205234.26 | 19309991.74 | 681444 | OR
661 | 81 | 070301 | Construction Cost Budget (CIP) | 14165790 | 13415930.36 | 749859.64 | 0 | OR
661 | 81 | 081204 | Construction Cost Budget (CIP) | 15435000 | 0 | 0 | 15435000 | OR
661 | 81 | 125131 | Construction Cost Budget (CIP) | 34465672 | 21600 | 8400 | 34435672 | OR
661 | 81 | 147101 | Construction Cost Budget (CIP) | 15000 | 3337.5 | 11662.5 | 0 | OR
661 | 81 | 160131 | Construction Cost Budget (CIP) | 45501743 | 43767744.25 | 1733998.75 | 0 | OR
661 | 81 | 184131 | Construction Cost Budget (CIP) | 50961226 | 31000 | 0 | 50930226 | OR
661 | 81 | 194101 | Construction Cost Budget (CIP) | 19491991 | 13082505.22 | 6065397.78 | 344088 | OR
661 | 81 | 256131 | Construction Cost Budget (CIP) | 42340000 | 0 | 42340000 | 0 | OR
661 | 81 | 021111 | Construction Contingency (CIP) | 227993 | 0 | 0 | 227993 | OR
661 | 81 | 042101 | Construction Contingency (CIP) | 498880 | 0 | 0 | 498880 | OR
661 | 81 | 044202 | Construction Contingency (CIP) | 1189832 | 0 | 0 | 1189832 | OR
661 | 81 | 045101 | Construction Contingency (CIP) | 732097 | 0 | 0 | 732097 | OR
661 | 81 | 048102 | Construction Contingency (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 051301 | Construction Contingency (CIP) | 710810 | 0 | 0 | 710810 | OR
661 | 81 | 052201 | Construction Contingency (CIP) | 659721 | 0 | 0 | 659721 | OR
661 | 81 | 053301 | Construction Contingency (CIP) | 606510 | 0 | 0 | 606510 | OR
661 | 81 | 056301 | Construction Contingency (CIP) | 661207 | 0 | 0 | 661207 | OR
661 | 81 | 058101 | Construction Contingency (CIP) | 2011035 | 0 | 0 | 2011035 | OR
661 | 81 | 060101 | Construction Contingency (CIP) | 844175 | 0 | 0 | 844175 | OR
661 | 81 | 061201 | Construction Contingency (CIP) | 679143 | 0 | 0 | 679143 | OR
661 | 81 | 070301 | Construction Contingency (CIP) | 387735 | 0 | 0 | 387735 | OR
661 | 81 | 081204 | Construction Contingency (CIP) | 350000 | 0 | 0 | 350000 | OR
661 | 81 | 160131 | Construction Contingency (CIP) | 804109 | 0 | 0 | 804109 | OR
661 | 81 | 184131 | Construction Contingency (CIP) | 804109 | 0 | 0 | 804109 | OR
661 | 81 | 194101 | Construction Contingency (CIP) | 341989 | 0 | 0 | 341989 | OR
661 | 81 | 256131 | Construction Contingency (CIP) | 900000 | 0 | 900000 | 0 | OR
661 | 81 | 021111 | Furniture, Fixture, & Equipment (CIP) | 562935 | 203945.07 | 324993.74 | 33996.19 | OR
661 | 81 | 044201 | Furniture, Fixture, & Equipment (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 044202 | Furniture, Fixture, & Equipment (CIP) | 3774227 | 0 | 0 | 3774227 | OR
661 | 81 | 045101 | Furniture, Fixture, & Equipment (CIP) | 2340161 | 1947914.52 | 230707.82 | 161538.66 | OR
661 | 81 | 048101 | Furniture, Fixture, & Equipment (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 048102 | Furniture, Fixture, & Equipment (CIP) | 4633747 | 0 | 0 | 4633747 | OR
661 | 81 | 049101 | Furniture, Fixture, & Equipment (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 050102 | Furniture, Fixture, & Equipment (CIP) | 3314725 | 0 | 0 | 3314725 | OR
661 | 81 | 051301 | Furniture, Fixture, & Equipment (CIP) | 2221383 | 707646.94 | 826475.48 | 687260.58 | OR
661 | 81 | 052201 | Furniture, Fixture, & Equipment (CIP) | 2061725 | 0 | 0 | 2061725 | OR
661 | 81 | 053301 | Furniture, Fixture, & Equipment (CIP) | 1895430 | 0 | 0 | 1895430 | OR
661 | 81 | 054301 | Furniture, Fixture, & Equipment (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 055201 | Furniture, Fixture, & Equipment (CIP) | 23500 | 0 | 23500 | 0 | OR
661 | 81 | 055202 | Furniture, Fixture, & Equipment (CIP) | 1372582 | 15173.23 | 261591.16 | 1095817.61 | OR
661 | 81 | 056301 | Furniture, Fixture, & Equipment (CIP) | 2066367 | 1615213.46 | 125052.98 | 326100.56 | OR
661 | 81 | 057201 | Furniture, Fixture, & Equipment (CIP) | 3030973 | 2040932.95 | 226665.79 | 763374.26 | OR
661 | 81 | 058101 | Furniture, Fixture, & Equipment (CIP) | 2619623 | 493244.39 | 1040456.86 | 1085921.75 | OR
661 | 81 | 059101 | Furniture, Fixture, & Equipment (CIP) | 1875609 | 602455.84 | 973642.49 | 299510.67 | OR
661 | 81 | 060101 | Furniture, Fixture, & Equipment (CIP) | 2638170 | 778091.92 | 899675.42 | 960402.66 | OR
661 | 81 | 061201 | Furniture, Fixture, & Equipment (CIP) | 2122419 | 1563990.83 | 53805.5 | 504622.67 | OR
661 | 81 | 070301 | Furniture, Fixture, & Equipment (CIP) | 1211729 | 0 | 303054.25 | 908674.75 | OR
661 | 81 | 125131 | Furniture, Fixture, & Equipment (CIP) | 1945945 | 0 | 0 | 1945945 | OR
661 | 81 | 160131 | Furniture, Fixture, & Equipment (CIP) | 1945945 | 0 | 0 | 1945945 | OR
661 | 81 | 184131 | Furniture, Fixture, & Equipment (CIP) | 1945945 | 0 | 0 | 1945945 | OR
661 | 81 | 194101 | Furniture, Fixture, & Equipment (CIP) | 1068765 | 0 | 80928 | 987837 | OR
661 | 81 | 256131 | Furniture, Fixture, & Equipment (CIP) | 106551 | 0 | 106550.31 | 0.69 | OR
661 | 81 | 021111 | Program Management (CIP) | 692334 | 158242.04 | 534091.96 | 0 | OR
661 | 81 | 042101 | Program Management (CIP) | 1437141 | 1056423 | 380718 | 0 | OR
661 | 81 | 044201 | Program Management (CIP) | 415876.76 | 0 | 415876.76 | 0 | OR
661 | 81 | 044202 | Program Management (CIP) | 3167430.56 | 3167430.56 | 0 | 0 | OR
661 | 81 | 045101 | Program Management (CIP) | 2815427 | 1041595.2 | 1773831.8 | 0 | OR
661 | 81 | 048101 | Program Management (CIP) | 303260.04 | 0 | 303260.04 | 0 | OR
661 | 81 | 048102 | Program Management (CIP) | 3634745.22 | 3634745.22 | 0 | 0 | OR
661 | 81 | 049101 | Program Management (CIP) | 159096.68 | 0 | 159096.68 | 0 | OR
661 | 81 | 050101 | Program Management (CIP) | 550737.43 | 0 | 550737.43 | 0 | OR
661 | 81 | 050102 | Program Management (CIP) | 2193312.01 | 1754649.61 | 438662.4 | 0 | OR
661 | 81 | 051301 | Program Management (CIP) | 2141500 | 767783.84 | 1373716.16 | 0 | OR
661 | 81 | 052201 | Program Management (CIP) | 2016982 | 1146587.5 | 870394.5 | 0 | OR
661 | 81 | 053301 | Program Management (CIP) | 1880248 | 1068858.8 | 811389.2 | 0 | OR
661 | 81 | 054301 | Program Management (CIP) | 570611.74 | 0 | 570611.74 | 0 | OR
661 | 81 | 055201 | Program Management (CIP) | 537854.52 | 0 | 537854.52 | 0 | OR
661 | 81 | 055202 | Program Management (CIP) | 1074798.48 | 1074798.48 | 0 | 0 | OR
661 | 81 | 056301 | Program Management (CIP) | 2012210 | 822012.13 | 1190197.87 | 0 | OR
661 | 81 | 057201 | Program Management (CIP) | 2910981 | 1320127.98 | 1590853.02 | 0 | OR
661 | 81 | 058101 | Program Management (CIP) | 2515729 | 449251.45 | 2066477.55 | 0 | OR
661 | 81 | 059101 | Program Management (CIP) | 1833356 | 455693.84 | 1377662.16 | 0 | OR
661 | 81 | 060101 | Program Management (CIP) | 2568522 | 651263.8 | 1917258.2 | 0 | OR
661 | 81 | 061201 | Program Management (CIP) | 2091660 | 697638.14 | 1394021.86 | 0 | OR
661 | 81 | 069101 | Program Management (CIP) | 321444.56 | 0 | 321444.56 | 0 | OR
661 | 81 | 070301 | Program Management (CIP) | 1196104 | 679945.6 | 516158.4 | 0 | OR
661 | 81 | 081204 | Program Management (CIP) | 801631 | 667837.35 | 133793.65 | 0 | OR
661 | 81 | 125131 | Program Management (CIP) | 2285981.04 | 1754505.52 | 531475.52 | 0 | OR
661 | 81 | 147101 | Program Management (CIP) | 122327.96 | 0 | 122327.96 | 0 | OR
661 | 81 | 160131 | Program Management (CIP) | 2382306 | 1360500.78 | 1021805.22 | 0 | OR
661 | 81 | 184131 | Program Management (CIP) | 1841363 | 1410861.75 | 430501.25 | 0 | OR
661 | 81 | 194101 | Program Management (CIP) | 1038500 | 476150.01 | 562349.99 | 0 | OR
661 | 81 | 256131 | Program Management (CIP) | 2446529 | 0 | 2446529 | 0 | OR
661 | 81 | 021111 | Technology (CIP) | 211621 | 18027.6 | 120996.95 | 72596.45 | OR
661 | 81 | 042101 | Technology (CIP) | 842280 | 0 | 61047.34 | 781232.66 | OR
661 | 81 | 044201 | Technology (CIP) | 198827.18 | 60724 | 128520.72 | 9582.46 | OR
661 | 81 | 044202 | Technology (CIP) | 2047256.79 | 0 | 86751.48 | 1960505.31 | OR
661 | 81 | 045101 | Technology (CIP) | 489403 | 63316.1 | 392340.15 | 33746.75 | OR
661 | 81 | 048101 | Technology (CIP) | 144310.05 | 0 | 0 | 144310.05 | OR
661 | 81 | 048102 | Technology (CIP) | 2286055.45 | 0 | 279532.56 | 2006522.89 | OR
661 | 81 | 049101 | Technology (CIP) | 86586.03 | 0 | 0 | 86586.03 | OR
661 | 81 | 050102 | Technology (CIP) | 1733660 | 0 | 273106.53 | 1460553.47 | OR
661 | 81 | 051301 | Technology (CIP) | 1033524 | 40521.3 | 308409.2 | 684593.5 | OR
661 | 81 | 052201 | Technology (CIP) | 1245180 | 0 | 128520.72 | 1116659.28 | OR
661 | 81 | 053301 | Technology (CIP) | 1030780 | 7088.66 | 118965.16 | 904726.18 | OR
661 | 81 | 054301 | Technology (CIP) | 133844.5 | 0 | 0 | 133844.5 | OR
661 | 81 | 055202 | Technology (CIP) | 729580 | 0 | 0 | 729580 | OR
661 | 81 | 056301 | Technology (CIP) | 1205080 | 10909 | 117367.66 | 1076803.34 | OR
661 | 81 | 057201 | Technology (CIP) | 1021776 | 38470.3 | 370249.54 | 613056.16 | OR
661 | 81 | 058101 | Technology (CIP) | 583597 | 31401.5 | 205710.88 | 346484.62 | OR
661 | 81 | 059101 | Technology (CIP) | 1033671 | 15553.4 | 256764.45 | 761353.15 | OR
661 | 81 | 060101 | Technology (CIP) | 1347702 | 41911 | 222143.02 | 1083647.98 | OR
661 | 81 | 061201 | Technology (CIP) | 1078830 | 41018.3 | 241904.99 | 795906.71 | OR
661 | 81 | 070301 | Technology (CIP) | 1013990 | 0 | 179929 | 834061 | OR
661 | 81 | 125131 | Technology (CIP) | 1500000 | 0 | 0 | 1500000 | OR
661 | 81 | 160131 | Technology (CIP) | 1200000 | 10595 | 0 | 1189405 | OR
661 | 81 | 184131 | Technology (CIP) | 1500000 | 0 | 0 | 1500000 | OR
661 | 81 | 194101 | Technology (CIP) | 378348 | 0 | 0 | 378348 | OR
661 | 81 | 256131 | JOC Contingency (CIP) | 25900 | 0 | 15958 | 9942 | OR
661 | 81 | 021111 | Commissioning (CIP) | 55200 | 27789 | 27411 | 0 | OR
661 | 81 | 042101 | Commissioning (CIP) | 30209 | 0 | 0 | 30209 | OR
661 | 81 | 044201 | Commissioning (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 044202 | Commissioning (CIP) | 77980 | 0 | 0 | 77980 | OR
661 | 81 | 045101 | Commissioning (CIP) | 67400 | 57700 | 9700 | 0 | OR
661 | 81 | 048101 | Commissioning (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 048102 | Commissioning (CIP) | 95739 | 0 | 0 | 95739 | OR
661 | 81 | 049101 | Commissioning (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 050102 | Commissioning (CIP) | 589284 | 0 | 0 | 589284 | OR
661 | 81 | 051301 | Commissioning (CIP) | 56000 | 39200 | 16800 | 0 | OR
661 | 81 | 052201 | Commissioning (CIP) | 42598 | 0 | 0 | 42598 | OR
661 | 81 | 053301 | Commissioning (CIP) | 39162 | 0 | 0 | 39162 | OR
661 | 81 | 054301 | Commissioning (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 055202 | Commissioning (CIP) | 277104 | 0 | 0 | 277104 | OR
661 | 81 | 056301 | Commissioning (CIP) | 68500 | 68500 | 0 | 0 | OR
661 | 81 | 057201 | Commissioning (CIP) | 82500 | 82500 | 0 | 0 | OR
661 | 81 | 058101 | Commissioning (CIP) | 54124 | 31300 | 3200 | 19624 | OR
661 | 81 | 059101 | Commissioning (CIP) | 38752 | 38400 | 0 | 352 | OR
661 | 81 | 060101 | Commissioning (CIP) | 130592 | 124062 | 6530 | 0 | OR
661 | 81 | 061201 | Commissioning (CIP) | 52400 | 52400 | 0 | 0 | OR
661 | 81 | 070301 | Commissioning (CIP) | 25036 | 0 | 0 | 25036 | OR
661 | 81 | 081204 | Commissioning (CIP) | 17500 | 0 | 0 | 17500 | OR
661 | 81 | 125131 | Commissioning (CIP) | 40205 | 0 | 0 | 40205 | OR
661 | 81 | 147101 | Commissioning (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 160131 | Commissioning (CIP) | 40205 | 27650 | 11850 | 705 | OR
661 | 81 | 184131 | Commissioning (CIP) | 40205 | 0 | 0 | 40205 | OR
661 | 81 | 194101 | Commissioning (CIP) | 62215 | 45976.88 | 16238.12 | 0 | OR
661 | 81 | 256131 | Commissioning (CIP) | 59900 | 0 | 59900 | 0 | OR
661 | 81 | 021111 | Geotechnical Engineering (CIP) | 15000 | 0 | 15000 | 0 | OR
661 | 81 | 042101 | Geotechnical Engineering (CIP) | 7000 | 0 | 7000 | 0 | OR
661 | 81 | 044201 | Geotechnical Engineering (CIP) | 47450 | 0 | 47450 | 0 | OR
661 | 81 | 044202 | Geotechnical Engineering (CIP) | 127800 | 99800 | 28000 | 0 | OR
661 | 81 | 045101 | Geotechnical Engineering (CIP) | 56400 | 0 | 56400 | 0 | OR
661 | 81 | 045102 | Geotechnical Engineering (CIP) | 14820 | 14820 | 0 | 0 | OR
661 | 81 | 048101 | Geotechnical Engineering (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 048102 | Geotechnical Engineering (CIP) | 9297 | 0 | 0 | 9297 | OR
661 | 81 | 049101 | Geotechnical Engineering (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 050101 | Geotechnical Engineering (CIP) | 21300 | 0 | 21300 | 0 | OR
661 | 81 | 050102 | Geotechnical Engineering (CIP) | 147321 | 0 | 23250 | 124071 | OR
661 | 81 | 051301 | Geotechnical Engineering (CIP) | 54970 | 0 | 54970 | 0 | OR
661 | 81 | 052201 | Geotechnical Engineering (CIP) | 36350 | 0 | 36350 | 0 | OR
661 | 81 | 053301 | Geotechnical Engineering (CIP) | 33075 | 0 | 33075 | 0 | OR
661 | 81 | 054301 | Geotechnical Engineering (CIP) | 23500 | 0 | 23500 | 0 | OR
661 | 81 | 055201 | Geotechnical Engineering (CIP) | 59550 | 0 | 59550 | 0 | OR
661 | 81 | 055202 | Geotechnical Engineering (CIP) | 69276 | 0 | 24250 | 45026 | OR
661 | 81 | 056301 | Geotechnical Engineering (CIP) | 40650 | 0 | 40650 | 0 | OR
661 | 81 | 057201 | Geotechnical Engineering (CIP) | 21255 | 0 | 21254.58 | 0.42 | OR
661 | 81 | 058101 | Geotechnical Engineering (CIP) | 24000 | 0 | 23000 | 1000 | OR
661 | 81 | 059101 | Geotechnical Engineering (CIP) | 21900 | 0 | 21900 | 0 | OR
661 | 81 | 060101 | Geotechnical Engineering (CIP) | 35190 | 0 | 35190 | 0 | OR
661 | 81 | 061201 | Geotechnical Engineering (CIP) | 48095 | 0 | 48095 | 0 | OR
661 | 81 | 069101 | Geotechnical Engineering (CIP) | 19600 | 0 | 19600 | 0 | OR
661 | 81 | 070301 | Geotechnical Engineering (CIP) | 48078 | 12200 | 35877.9 | 0.1 | OR
661 | 81 | 081204 | Geotechnical Engineering (CIP) | 3500 | 0 | 0 | 3500 | OR
661 | 81 | 125131 | Geotechnical Engineering (CIP) | 36040 | 6396.5 | 29643.5 | 0 | OR
661 | 81 | 147101 | Geotechnical Engineering (CIP) | 7312 | 0 | 7312 | 0 | OR
661 | 81 | 160131 | Geotechnical Engineering (CIP) | 41300 | 0 | 41300 | 0 | OR
661 | 81 | 184131 | Geotechnical Engineering (CIP) | 44286 | 21840 | 22446 | 0 | OR
661 | 81 | 194101 | Geotechnical Engineering (CIP) | 75135 | 29780 | 45355 | 0 | OR
661 | 81 | 021111 | Hazmat Consulting (CIP) | 290625 | 90842.5 | 199782.5 | 0 | OR
661 | 81 | 042101 | Hazmat Consulting (CIP) | 16375 | 0 | 13112.63 | 3262.37 | OR
661 | 81 | 044201 | Hazmat Consulting (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 044202 | Hazmat Consulting (CIP) | 23688 | 23688 | 0 | 0 | OR
661 | 81 | 045101 | Hazmat Consulting (CIP) | 71572 | 16352 | 55220 | 0 | OR
661 | 81 | 048101 | Hazmat Consulting (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 048102 | Hazmat Consulting (CIP) | 10626 | 0 | 0 | 10626 | OR
661 | 81 | 049101 | Hazmat Consulting (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 050101 | Hazmat Consulting (CIP) | 6970 | 0 | 6970 | 0 | OR
661 | 81 | 050102 | Hazmat Consulting (CIP) | 147321 | 0 | 0 | 147321 | OR
661 | 81 | 051301 | Hazmat Consulting (CIP) | 110835 | 13799.5 | 94495.5 | 2540 | OR
661 | 81 | 052201 | Hazmat Consulting (CIP) | 124617 | 109008.75 | 15607.5 | 0.75 | OR
661 | 81 | 053301 | Hazmat Consulting (CIP) | 12300 | 0 | 12300 | 0 | OR
661 | 81 | 054301 | Hazmat Consulting (CIP) | 17015 | 0 | 5255 | 11760 | OR
661 | 81 | 055201 | Hazmat Consulting (CIP) | 15725 | 0 | 15725 | 0 | OR
661 | 81 | 055202 | Hazmat Consulting (CIP) | 69276 | 18463.9 | 19026.1 | 31786 | OR
661 | 81 | 056301 | Hazmat Consulting (CIP) | 162230 | 63550 | 96960 | 1720 | OR
661 | 81 | 057201 | Hazmat Consulting (CIP) | 187275 | 103850 | 76735 | 6690 | OR
661 | 81 | 058101 | Hazmat Consulting (CIP) | 34725 | 11449 | 23276 | 0 | OR
661 | 81 | 059101 | Hazmat Consulting (CIP) | 101905 | 35230 | 66675 | 0 | OR
661 | 81 | 060101 | Hazmat Consulting (CIP) | 188433 | 51029 | 137404 | 0 | OR
661 | 81 | 061201 | Hazmat Consulting (CIP) | 126845 | 81025 | 45820 | 0 | OR
661 | 81 | 070301 | Hazmat Consulting (CIP) | 11030 | 4030 | 7000 | 0 | OR
661 | 81 | 125131 | Hazmat Consulting (CIP) | 98835 | 38649.5 | 60185.5 | 0 | OR
661 | 81 | 147101 | Hazmat Consulting (CIP) | 12445 | 0 | 12445 | 0 | OR
661 | 81 | 160131 | Hazmat Consulting (CIP) | 96645 | 72115 | 24530 | 0 | OR
661 | 81 | 184131 | Hazmat Consulting (CIP) | 17427 | 17427 | 0 | 0 | OR
661 | 81 | 194101 | Hazmat Consulting (CIP) | 147631 | 119835.62 | 27794.72 | 0.66 | OR
661 | 81 | 021111 | Holding - Project Contingency (CIP) | 261571 | 0 | 0 | 261571 | OR
661 | 81 | 042101 | Holding - Project Contingency (CIP) | 735159 | 0 | 0 | 735159 | OR
661 | 81 | 044201 | Holding - Project Contingency (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 044202 | Holding - Project Contingency (CIP) | 2247684 | 0 | 0 | 2247684 | OR
661 | 81 | 045101 | Holding - Project Contingency (CIP) | 5258227 | 0 | 0 | 5258227 | OR
661 | 81 | 048101 | Holding - Project Contingency (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 048102 | Holding - Project Contingency (CIP) | 3673930.74 | 0 | 0 | 3673930.74 | OR
661 | 81 | 049101 | Holding - Project Contingency (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 050102 | Holding - Project Contingency (CIP) | 3569047.55 | 0 | 0 | 3569047.55 | OR
661 | 81 | 051301 | Holding - Project Contingency (CIP) | 470194 | 0 | 0 | 470194 | OR
661 | 81 | 052201 | Holding - Project Contingency (CIP) | 450126 | 0 | 0 | 450126 | OR
661 | 81 | 053301 | Holding - Project Contingency (CIP) | 884806 | 0 | 0 | 884806 | OR
661 | 81 | 054301 | Holding - Project Contingency (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 055202 | Holding - Project Contingency (CIP) | 4774240 | 0 | 0 | 4774240 | OR
661 | 81 | 056301 | Holding - Project Contingency (CIP) | 392585 | 0 | 0 | 392585 | OR
661 | 81 | 057201 | Holding - Project Contingency (CIP) | 820968 | 0 | 0 | 820968 | OR
661 | 81 | 058101 | Holding - Project Contingency (CIP) | 710215 | 0 | 0 | 710215 | OR
661 | 81 | 059101 | Holding - Project Contingency (CIP) | 599042 | 0 | 0 | 599042 | OR
661 | 81 | 060101 | Holding - Project Contingency (CIP) | 733907 | 0 | 0 | 733907 | OR
661 | 81 | 061201 | Holding - Project Contingency (CIP) | 273066 | 0 | 0 | 273066 | OR
661 | 81 | 070301 | Holding - Project Contingency (CIP) | 458805 | 0 | 0 | 458805 | OR
661 | 81 | 081204 | Holding - Project Contingency (CIP) | 343323 | 0 | 0 | 343323 | OR
661 | 81 | 125131 | Holding - Project Contingency (CIP) | 1311750.96 | 0 | 0 | 1311750.96 | OR
661 | 81 | 147101 | Holding - Project Contingency (CIP) | 161146.04 | 0 | 0 | 161146.04 | OR
661 | 81 | 160131 | Holding - Project Contingency (CIP) | 3082769 | 0 | 0 | 3082769 | OR
661 | 81 | 184131 | Holding - Project Contingency (CIP) | 3955095 | 0 | 0 | 3955095 | OR
661 | 81 | 194101 | Holding - Project Contingency (CIP) | 170244 | 0 | 0 | 170244 | OR
661 | 81 | 256131 | Holding - Project Contingency (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 021111 | Abatement/Hazmat Contingency (CIP) | 40555 | 0 | 0 | 40555 | OR
661 | 81 | 042101 | Abatement/Hazmat Contingency (CIP) | 33934 | 0 | 0 | 33934 | OR
661 | 81 | 044201 | Abatement/Hazmat Contingency (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 044202 | Abatement/Hazmat Contingency (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 045101 | Abatement/Hazmat Contingency (CIP) | 55150 | 14618 | 0 | 40532 | OR
661 | 81 | 048101 | Abatement/Hazmat Contingency (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 048102 | Abatement/Hazmat Contingency (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 049101 | Abatement/Hazmat Contingency (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 051301 | Abatement/Hazmat Contingency (CIP) | 7150 | 0 | 0 | 7150 | OR
661 | 81 | 052201 | Abatement/Hazmat Contingency (CIP) | 49582 | 0 | 0 | 49582 | OR
661 | 81 | 053301 | Abatement/Hazmat Contingency (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 054301 | Abatement/Hazmat Contingency (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 055202 | Abatement/Hazmat Contingency (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 056301 | Abatement/Hazmat Contingency (CIP) | 53137 | 0 | 0 | 53137 | OR
661 | 81 | 057201 | Abatement/Hazmat Contingency (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 058101 | Abatement/Hazmat Contingency (CIP) | 48699 | 0 | 0 | 48699 | OR
661 | 81 | 059101 | Abatement/Hazmat Contingency (CIP) | 50263 | 0 | 0 | 50263 | OR
661 | 81 | 060101 | Abatement/Hazmat Contingency (CIP) | 80820 | 0 | 0 | 80820 | OR
661 | 81 | 061201 | Abatement/Hazmat Contingency (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 070301 | Abatement/Hazmat Contingency (CIP) | 19831 | 0 | 0 | 19831 | OR
661 | 81 | 194101 | Abatement/Hazmat Contingency (CIP) | 31520 | 0 | 0 | 31520 | OR
661 | 81 | 000000 | Insurance/Surety (CIP)(Admin) | 375000 | 112500 | 187500 | 75000 | ISD
661 | 81 | 021111 | Job Order Contract (CIP) | 13949 | 0 | 13949 | 0 | OR
661 | 81 | 045102 | Job Order Contract (CIP) | 4070000 | 0 | 3954753.09 | 115246.91 | OR
661 | 81 | 050102 | Job Order Contract (CIP) | 412499 | 0 | 0 | 412499 | OR
661 | 81 | 054312 | Job Order Contract (CIP) | 1208869.26 | 0 | 1208869.26 | 0 | OR
661 | 81 | 055201 | Job Order Contract (CIP) | 5521.5 | 0 | 5521.5 | 0 | OR
661 | 81 | 055202 | Job Order Contract (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 256131 | Job Order Contract (CIP) | 243100 | 0 | 243100 | 0 | OR
661 | 81 | 021111 | Moving (CIP) | 123015 | 35942.51 | 87071.9 | 0.59 | OR
661 | 81 | 042101 | Moving (CIP) | 30402 | 3950 | 0 | 26452 | OR
661 | 81 | 044201 | Moving (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 044202 | Moving (CIP) | 78479 | 0 | 0 | 78479 | OR
661 | 81 | 045101 | Moving (CIP) | 250787 | 222445.38 | 28341.48 | 0.14 | OR
661 | 81 | 045102 | Moving (CIP) | 19744 | 8396.5 | 11347 | 0.5 | OR
661 | 81 | 048101 | Moving (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 048102 | Moving (CIP) | 96352 | 0 | 0 | 96352 | OR
661 | 81 | 049101 | Moving (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 050102 | Moving (CIP) | 589284 | 0 | 0 | 589284 | OR
661 | 81 | 051301 | Moving (CIP) | 162536 | 56319.02 | 106194.98 | 22 | OR
661 | 81 | 052201 | Moving (CIP) | 42870 | 0 | 0 | 42870 | OR
661 | 81 | 053301 | Moving (CIP) | 39412 | 0 | 0 | 39412 | OR
661 | 81 | 054301 | Moving (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 055202 | Moving (CIP) | 277104 | 18410 | 21755 | 236939 | OR
661 | 81 | 056301 | Moving (CIP) | 191972 | 122994.64 | 68977.1 | 0.26 | OR
661 | 81 | 057201 | Moving (CIP) | 81590 | 19937.63 | 61651.57 | 0.8 | OR
661 | 81 | 058101 | Moving (CIP) | 132384 | 43650.4 | 88732.64 | 0.96 | OR
661 | 81 | 059101 | Moving (CIP) | 74790 | 47132.5 | 27657 | 0.5 | OR
661 | 81 | 060101 | Moving (CIP) | 143424 | 60537.87 | 82885.43 | 0.7 | OR
661 | 81 | 061201 | Moving (CIP) | 44132 | 9250.7 | 13175 | 21706.3 | OR
661 | 81 | 070301 | Moving (CIP) | 99896 | 93942 | 5954 | 0 | OR
661 | 81 | 081204 | Moving (CIP) | 17612 | 0 | 0 | 17612 | OR
661 | 81 | 125131 | Moving (CIP) | 51440 | 17300 | 34140 | 0 | OR
661 | 81 | 147101 | Moving (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 160131 | Moving (CIP) | 40463 | 0 | 2121.06 | 38341.94 | OR
661 | 81 | 184131 | Moving (CIP) | 40463 | 0 | 0 | 40463 | OR
661 | 81 | 194101 | Moving (CIP) | 47629 | 46512 | 1117 | 0 | OR
661 | 81 | 256131 | Moving (CIP) | 22878.5 | 0 | 15688 | 7190.5 | OR
661 | 81 | 021111 | Material Testing (CIP) | 40995 | 5711.5 | 35283.5 | 0 | OR
661 | 81 | 042101 | Material Testing (CIP) | 30209 | 0 | 0 | 30209 | OR
661 | 81 | 044201 | Material Testing (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 044202 | Material Testing (CIP) | 77980 | 0 | 0 | 77980 | OR
661 | 81 | 045101 | Material Testing (CIP) | 113649 | 35138.12 | 78510.88 | 0 | OR
661 | 81 | 048101 | Material Testing (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 048102 | Material Testing (CIP) | 95739 | 0 | 0 | 95739 | OR
661 | 81 | 049101 | Material Testing (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 050102 | Material Testing (CIP) | 147321 | 0 | 0 | 147321 | OR
661 | 81 | 051301 | Material Testing (CIP) | 110513 | 66146.25 | 44366.25 | 0.5 | OR
661 | 81 | 052201 | Material Testing (CIP) | 42598 | 0 | 0 | 42598 | OR
661 | 81 | 053301 | Material Testing (CIP) | 134993 | 134993 | 0 | 0 | OR
661 | 81 | 054301 | Material Testing (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 055202 | Material Testing (CIP) | 69276 | 0 | 0 | 69276 | OR
661 | 81 | 056301 | Material Testing (CIP) | 64913 | 30859.12 | 34053.88 | 0 | OR
661 | 81 | 057201 | Material Testing (CIP) | 209893 | 209150.5 | 742.5 | 0 | OR
661 | 81 | 058101 | Material Testing (CIP) | 69114 | 13960.25 | 55153.25 | 0.5 | OR
661 | 81 | 059101 | Material Testing (CIP) | 116070 | 72732.49 | 43337.51 | 0 | OR
661 | 81 | 060101 | Material Testing (CIP) | 91750 | 0 | 91715 | 35 | OR
661 | 81 | 061201 | Material Testing (CIP) | 72472 | 42584.77 | 29886.83 | 0.4 | OR
661 | 81 | 070301 | Material Testing (CIP) | 25036 | 0 | 0 | 25036 | OR
661 | 81 | 081204 | Material Testing (CIP) | 17500 | 0 | 0 | 17500 | OR
661 | 81 | 125131 | Material Testing (CIP) | 40205 | 0 | 0 | 40205 | OR
661 | 81 | 147101 | Material Testing (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 160131 | Material Testing (CIP) | 149889 | 149889 | 0 | 0 | OR
661 | 81 | 184131 | Material Testing (CIP) | 40205 | 0 | 0 | 40205 | OR
661 | 81 | 194101 | Material Testing (CIP) | 61366 | 60829.25 | 535.9 | 0.85 | OR
661 | 81 | 256131 | Material Testing (CIP) | 38725.1 | 0 | 38725.1 | 0 | OR
661 | 81 | 044201 | Other Engineering Services (CIP) | 6500 | 0 | 0 | 6500 | OR
661 | 81 | 044202 | Other Engineering Services (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 048102 | Other Engineering Services (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 050102 | Other Engineering Services (CIP) | 73661 | 25000 | 0 | 48661 | OR
661 | 81 | 051301 | Other Engineering Services (CIP) | 19500 | 0 | 19500 | 0 | OR
661 | 81 | 052201 | Other Engineering Services (CIP) | 46750 | 0 | 22450 | 24300 | OR
661 | 81 | 055201 | Other Engineering Services (CIP) | 3000 | 0 | 3000 | 0 | OR
661 | 81 | 055202 | Other Engineering Services (CIP) | 34638 | 0 | 0 | 34638 | OR
661 | 81 | 057201 | Other Engineering Services (CIP) | 25000 | 0 | 25000 | 0 | OR
661 | 81 | 058101 | Other Engineering Services (CIP) | 23720 | 0 | 23720 | 0 | OR
661 | 81 | 059101 | Other Engineering Services (CIP) | 4000 | 0 | 0 | 4000 | OR
661 | 81 | 125131 | Other Engineering Services (CIP) | 74060 | 16800 | 57260 | 0 | OR
661 | 81 | 160131 | Other Engineering Services (CIP) | 18200 | 0 | 18200 | 0 | OR
661 | 81 | 184131 | Other Engineering Services (CIP) | 13950 | 13950 | 0 | 0 | OR
661 | 81 | 000000 | Printing (CIP)(Admin) | 50000 | 37136.86 | 7863.14 | 5000 | ISD
661 | 81 | 021111 | Architect/Engineering Reimbursables (CIP) | 6477 | 5000 | 0 | 1477 | OR
661 | 81 | 042101 | Architect/Engineering Reimbursables (CIP) | 38510 | 33822.5 | 4687.5 | 0 | OR
661 | 81 | 044201 | Architect/Engineering Reimbursables (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 044202 | Architect/Engineering Reimbursables (CIP) | 24312 | 0 | 0 | 24312 | OR
661 | 81 | 045101 | Architect/Engineering Reimbursables (CIP) | 9799 | 5000 | 0 | 4799 | OR
661 | 81 | 045102 | Architect/Engineering Reimbursables (CIP) | 5000 | 4388.34 | 611.66 | 0 | OR
661 | 81 | 048101 | Architect/Engineering Reimbursables (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 048102 | Architect/Engineering Reimbursables (CIP) | 32125 | 0 | 0 | 32125 | OR
661 | 81 | 049101 | Architect/Engineering Reimbursables (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 050101 | Architect/Engineering Reimbursables (CIP) | 807 | 0 | 807 | 0 | OR
661 | 81 | 050102 | Architect/Engineering Reimbursables (CIP) | 36830 | 4404.17 | 4225.06 | 28200.77 | OR
661 | 81 | 051301 | Architect/Engineering Reimbursables (CIP) | 20194 | 2549.74 | 2450.26 | 15194 | OR
661 | 81 | 052201 | Architect/Engineering Reimbursables (CIP) | 18743 | 1445.46 | 3554.54 | 13743 | OR
661 | 81 | 053301 | Architect/Engineering Reimbursables (CIP) | 17231 | 101 | 4899 | 12231 | OR
661 | 81 | 054301 | Architect/Engineering Reimbursables (CIP) | 230 | 0 | 229.19 | 0.81 | OR
661 | 81 | 055201 | Architect/Engineering Reimbursables (CIP) | 5000 | 0 | 3034.12 | 1965.88 | OR
661 | 81 | 055202 | Architect/Engineering Reimbursables (CIP) | 20000 | 4828.26 | 171.74 | 15000 | OR
661 | 81 | 056301 | Architect/Engineering Reimbursables (CIP) | 18785 | 5000 | 7912.47 | 5872.53 | OR
661 | 81 | 057201 | Architect/Engineering Reimbursables (CIP) | 27554 | 0 | 7000 | 20554 | OR
661 | 81 | 058101 | Architect/Engineering Reimbursables (CIP) | 23815 | 8500 | 0 | 15315 | OR
661 | 81 | 059101 | Architect/Engineering Reimbursables (CIP) | 17051 | 2129.09 | 2870.91 | 12051 | OR
661 | 81 | 060101 | Architect/Engineering Reimbursables (CIP) | 23983 | 1474.64 | 3525.36 | 18983 | OR
661 | 81 | 061201 | Architect/Engineering Reimbursables (CIP) | 19295 | 1013.13 | 3986.87 | 14295 | OR
661 | 81 | 070301 | Architect/Engineering Reimbursables (CIP) | 11016 | 2030.87 | 2969.13 | 6016 | OR
661 | 81 | 081204 | Architect/Engineering Reimbursables (CIP) | 7700 | 5000 | 0 | 2700 | OR
661 | 81 | 125131 | Architect/Engineering Reimbursables (CIP) | 17690 | 4025.2 | 974.8 | 12690 | OR
661 | 81 | 147101 | Architect/Engineering Reimbursables (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 160131 | Architect/Engineering Reimbursables (CIP) | 17690 | 4182.59 | 4817.41 | 8690 | OR
661 | 81 | 184131 | Architect/Engineering Reimbursables (CIP) | 17690 | 4830.13 | 169.87 | 12690 | OR
661 | 81 | 194101 | Architect/Engineering Reimbursables (CIP) | 9716 | 4133.47 | 866.53 | 4716 | OR
661 | 81 | 256131 | Architect/Engineering Reimbursables (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 021111 | Roof Consulting (CIP) | 11777 | 0 | 0 | 11777 | OR
661 | 81 | 042101 | Roof Consulting (CIP) | 24167 | 0 | 0 | 24167 | OR
661 | 81 | 044201 | Roof Consulting (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 044202 | Roof Consulting (CIP) | 62384 | 0 | 0 | 62384 | OR
661 | 81 | 045101 | Roof Consulting (CIP) | 85700 | 68300 | 17400 | 0 | OR
661 | 81 | 048101 | Roof Consulting (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 048102 | Roof Consulting (CIP) | 76591 | 0 | 0 | 76591 | OR
661 | 81 | 049101 | Roof Consulting (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 050102 | Roof Consulting (CIP) | 147321 | 0 | 0 | 147321 | OR
661 | 81 | 051301 | Roof Consulting (CIP) | 81200 | 56300 | 24900 | 0 | OR
661 | 81 | 052201 | Roof Consulting (CIP) | 34078 | 0 | 0 | 34078 | OR
661 | 81 | 053301 | Roof Consulting (CIP) | 31329 | 0 | 0 | 31329 | OR
661 | 81 | 054301 | Roof Consulting (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 055201 | Roof Consulting (CIP) | 11500 | 0 | 11500 | 0 | OR
661 | 81 | 055202 | Roof Consulting (CIP) | 69276 | 0 | 0 | 69276 | OR
661 | 81 | 056301 | Roof Consulting (CIP) | 74700 | 62577.35 | 12122.65 | 0 | OR
661 | 81 | 057201 | Roof Consulting (CIP) | 50099 | 0 | 0 | 50099 | OR
661 | 81 | 058101 | Roof Consulting (CIP) | 43300 | 0 | 0 | 43300 | OR
661 | 81 | 059101 | Roof Consulting (CIP) | 35000 | 26600 | 8400 | 0 | OR
661 | 81 | 060101 | Roof Consulting (CIP) | 43606 | 0 | 0 | 43606 | OR
661 | 81 | 061201 | Roof Consulting (CIP) | 35081 | 5000 | 20950 | 9131 | OR
661 | 81 | 070301 | Roof Consulting (CIP) | 20029 | 0 | 0 | 20029 | OR
661 | 81 | 081204 | Roof Consulting (CIP) | 14000 | 0 | 0 | 14000 | OR
661 | 81 | 125131 | Roof Consulting (CIP) | 32164 | 0 | 0 | 32164 | OR
661 | 81 | 147101 | Roof Consulting (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 160131 | Roof Consulting (CIP) | 40000 | 40000 | 0 | 0 | OR
661 | 81 | 184131 | Roof Consulting (CIP) | 32164 | 0 | 0 | 32164 | OR
661 | 81 | 194101 | Roof Consulting (CIP) | 38500 | 3850 | 34650 | 0 | OR
661 | 81 | 256131 | Roof Consulting (CIP) | 98200 | 0 | 98200 | 0 | OR
661 | 81 | 021111 | Permit/Fee Reimbursement (CIP) | 7834 | 0 | 57 | 7777 | OR
661 | 81 | 042101 | Permit/Fee Reimbursement (CIP) | 48334 | 0 | 0 | 48334 | OR
661 | 81 | 044201 | Permit/Fee Reimbursement (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 044202 | Permit/Fee Reimbursement (CIP) | 124768 | 0 | 0 | 124768 | OR
661 | 81 | 045101 | Permit/Fee Reimbursement (CIP) | 77361 | 0 | 660 | 76701 | OR
661 | 81 | 048101 | Permit/Fee Reimbursement (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 048102 | Permit/Fee Reimbursement (CIP) | 153182 | 0 | 0 | 153182 | OR
661 | 81 | 049101 | Permit/Fee Reimbursement (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 050102 | Permit/Fee Reimbursement (CIP) | 73661 | 0 | 0 | 73661 | OR
661 | 81 | 051301 | Permit/Fee Reimbursement (CIP) | 73434 | 0 | 0 | 73434 | OR
661 | 81 | 052201 | Permit/Fee Reimbursement (CIP) | 68156 | 0 | 0 | 68156 | OR
661 | 81 | 053301 | Permit/Fee Reimbursement (CIP) | 62659 | 0 | 0 | 62659 | OR
661 | 81 | 054301 | Permit/Fee Reimbursement (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 055202 | Permit/Fee Reimbursement (CIP) | 55169 | 0 | 0 | 55169 | OR
661 | 81 | 056301 | Permit/Fee Reimbursement (CIP) | 68310 | 0 | 660 | 67650 | OR
661 | 81 | 057201 | Permit/Fee Reimbursement (CIP) | 100197 | 0 | 1377 | 98820 | OR
661 | 81 | 058101 | Permit/Fee Reimbursement (CIP) | 86599 | 0 | 990 | 85609 | OR
661 | 81 | 059101 | Permit/Fee Reimbursement (CIP) | 62004 | 0 | 243 | 61761 | OR
661 | 81 | 060101 | Permit/Fee Reimbursement (CIP) | 87212 | 0 | 62 | 87150 | OR
661 | 81 | 061201 | Permit/Fee Reimbursement (CIP) | 70163 | 330 | 903 | 68930 | OR
661 | 81 | 070301 | Permit/Fee Reimbursement (CIP) | 40057 | 0 | 0 | 40057 | OR
661 | 81 | 081204 | Permit/Fee Reimbursement (CIP) | 28000 | 0 | 0 | 28000 | OR
661 | 81 | 125131 | Permit/Fee Reimbursement (CIP) | 47049 | 0 | 423 | 46626 | OR
661 | 81 | 147101 | Permit/Fee Reimbursement (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 160131 | Permit/Fee Reimbursement (CIP) | 64329 | 0 | 330 | 63999 | OR
661 | 81 | 184131 | Permit/Fee Reimbursement (CIP) | 64329 | 0 | 0 | 64329 | OR
661 | 81 | 194101 | Permit/Fee Reimbursement (CIP) | 35331 | 0 | 0 | 35331 | OR
661 | 81 | 256131 | Permit/Fee Reimbursement (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 021111 | Surveying (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 042101 | Surveying (CIP) | 54375 | 0 | 13022 | 41353 | OR
661 | 81 | 044201 | Surveying (CIP) | 50282.5 | 0 | 30120 | 20162.5 | OR
661 | 81 | 044202 | Surveying (CIP) | 90081.5 | 0 | 0 | 90081.5 | OR
661 | 81 | 045101 | Surveying (CIP) | 9110 | 0 | 5000 | 4110 | OR
661 | 81 | 048101 | Surveying (CIP) | 53720 | 0 | 0 | 53720 | OR
661 | 81 | 048102 | Surveying (CIP) | 72965 | 72965 | 0 | 0 | OR
661 | 81 | 049101 | Surveying (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 050101 | Surveying (CIP) | 18310 | 0 | 18310 | 0 | OR
661 | 81 | 050102 | Surveying (CIP) | 147321 | 5956 | 8934 | 132431 | OR
661 | 81 | 051301 | Surveying (CIP) | 82614 | 5640 | 65897.15 | 11076.85 | OR
661 | 81 | 052201 | Surveying (CIP) | 83986 | 9212.5 | 74773.25 | 0.25 | OR
661 | 81 | 053301 | Surveying (CIP) | 70491 | 6880 | 40050 | 23561 | OR
661 | 81 | 054301 | Surveying (CIP) | 51007 | 0 | 32730.95 | 18276.05 | OR
661 | 81 | 055201 | Surveying (CIP) | 25670 | 0 | 25670 | 0 | OR
661 | 81 | 055202 | Surveying (CIP) | 69276 | 26600 | 23880 | 18796 | OR
661 | 81 | 056301 | Surveying (CIP) | 76848 | 12020 | 23840 | 40988 | OR
661 | 81 | 057201 | Surveying (CIP) | 171610 | 9615.19 | 161994.54 | 0.27 | OR
661 | 81 | 058101 | Surveying (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 059101 | Surveying (CIP) | 23251 | 0 | 0 | 23251 | OR
661 | 81 | 060101 | Surveying (CIP) | 32705 | 0 | 0 | 32705 | OR
661 | 81 | 061201 | Surveying (CIP) | 78933 | 0 | 32685 | 46248 | OR
661 | 81 | 069101 | Surveying (CIP) | 32714.5 | 0 | 32714.5 | 0 | OR
661 | 81 | 070301 | Surveying (CIP) | 45063 | 0 | 32900 | 12163 | OR
661 | 81 | 081204 | Surveying (CIP) | 31500 | 0 | 0 | 31500 | OR
661 | 81 | 125131 | Surveying (CIP) | 28000 | 22500 | 5500 | 0 | OR
661 | 81 | 147101 | Surveying (CIP) | 24038.5 | 0 | 24038.5 | 0 | OR
661 | 81 | 160131 | Surveying (CIP) | 3828 | 0 | 0 | 3828 | OR
661 | 81 | 184131 | Surveying (CIP) | 24123 | 0 | 0 | 24123 | OR
661 | 81 | 194101 | Surveying (CIP) | 65127 | 0 | 65126.6 | 0.4 | OR
661 | 81 | 021111 | Traffic Impact Analysis & Traffic Management Planning (CIP) | 50000 | 0 | 48250 | 1750 | OR
661 | 81 | 042101 | Traffic Impact Analysis & Traffic Management Planning (CIP) | 50000 | 2000 | 8800 | 39200 | OR
661 | 81 | 044201 | Traffic Impact Analysis & Traffic Management Planning (CIP) | 48250 | 0 | 23450 | 24800 | OR
661 | 81 | 044202 | Traffic Impact Analysis & Traffic Management Planning (CIP) | 51750 | 40800 | 5200 | 5750 | OR
661 | 81 | 045101 | Traffic Impact Analysis & Traffic Management Planning (CIP) | 50000 | 2624.5 | 24675.5 | 22700 | OR
661 | 81 | 048101 | Traffic Impact Analysis & Traffic Management Planning (CIP) | 27800 | 0 | 0 | 27800 | OR
661 | 81 | 048102 | Traffic Impact Analysis & Traffic Management Planning (CIP) | 51000 | 51000 | 0 | 0 | OR
661 | 81 | 049101 | Traffic Impact Analysis & Traffic Management Planning (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 050102 | Traffic Impact Analysis & Traffic Management Planning (CIP) | 73661 | 3223.25 | 31341.75 | 39096 | OR
661 | 81 | 051301 | Traffic Impact Analysis & Traffic Management Planning (CIP) | 50000 | 0 | 25500 | 24500 | OR
661 | 81 | 052201 | Traffic Impact Analysis & Traffic Management Planning (CIP) | 50000 | 2747.5 | 24052.5 | 23200 | OR
661 | 81 | 053301 | Traffic Impact Analysis & Traffic Management Planning (CIP) | 50000 | 3550 | 27750 | 18700 | OR
661 | 81 | 054301 | Traffic Impact Analysis & Traffic Management Planning (CIP) | 25500 | 0 | 25500 | 0 | OR
661 | 81 | 055201 | Traffic Impact Analysis & Traffic Management Planning (CIP) | 25500 | 0 | 25500 | 0 | OR
661 | 81 | 055202 | Traffic Impact Analysis & Traffic Management Planning (CIP) | 34638 | 7855.7 | 21294.3 | 5488 | OR
661 | 81 | 056301 | Traffic Impact Analysis & Traffic Management Planning (CIP) | 50000 | 0 | 48250 | 1750 | OR
661 | 81 | 057201 | Traffic Impact Analysis & Traffic Management Planning (CIP) | 50000 | 0 | 48250 | 1750 | OR
661 | 81 | 058101 | Traffic Impact Analysis & Traffic Management Planning (CIP) | 50000 | 0 | 25500 | 24500 | OR
661 | 81 | 059101 | Traffic Impact Analysis & Traffic Management Planning (CIP) | 50000 | 0 | 25500 | 24500 | OR
661 | 81 | 060101 | Traffic Impact Analysis & Traffic Management Planning (CIP) | 50000 | 0 | 25500 | 24500 | OR
661 | 81 | 061201 | Traffic Impact Analysis & Traffic Management Planning (CIP) | 50000 | 3161.5 | 24638.5 | 22200 | OR
661 | 81 | 070301 | Traffic Impact Analysis & Traffic Management Planning (CIP) | 50000 | 0 | 48250 | 1750 | OR
661 | 81 | 081204 | Traffic Impact Analysis & Traffic Management Planning (CIP) | 50000 | 0 | 0 | 50000 | OR
661 | 81 | 125131 | Traffic Impact Analysis & Traffic Management Planning (CIP) | 133750 | 0 | 92750 | 41000 | OR
661 | 81 | 147101 | Traffic Impact Analysis & Traffic Management Planning (CIP) | 46750 | 0 | 46750 | 0 | OR
661 | 81 | 160131 | Traffic Impact Analysis & Traffic Management Planning (CIP) | 50000 | 0 | 26176.75 | 23823.25 | OR
661 | 81 | 184131 | Traffic Impact Analysis & Traffic Management Planning (CIP) | 50000 | 28434 | 9366 | 12200 | OR
661 | 81 | 194101 | Traffic Impact Analysis & Traffic Management Planning (CIP) | 50000 | 0 | 25500 | 24500 | OR
661 | 81 | 021111 | Test and Balancing (CIP) | 34460 | 25845 | 8615 | 0 | OR
661 | 81 | 042101 | Test and Balancing (CIP) | 30209 | 0 | 0 | 30209 | OR
661 | 81 | 044201 | Test and Balancing (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 044202 | Test and Balancing (CIP) | 77980 | 0 | 0 | 77980 | OR
661 | 81 | 045101 | Test and Balancing (CIP) | 123762 | 95554.24 | 28207.39 | 0.37 | OR
661 | 81 | 048101 | Test and Balancing (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 048102 | Test and Balancing (CIP) | 95739 | 0 | 0 | 95739 | OR
661 | 81 | 049101 | Test and Balancing (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 050102 | Test and Balancing (CIP) | 294642 | 0 | 0 | 294642 | OR
661 | 81 | 051301 | Test and Balancing (CIP) | 96195 | 96195 | 0 | 0 | OR
661 | 81 | 052201 | Test and Balancing (CIP) | 42598 | 0 | 0 | 42598 | OR
661 | 81 | 053301 | Test and Balancing (CIP) | 39162 | 0 | 0 | 39162 | OR
661 | 81 | 054301 | Test and Balancing (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 055202 | Test and Balancing (CIP) | 138552 | 0 | 0 | 138552 | OR
661 | 81 | 056301 | Test and Balancing (CIP) | 59591 | 59591 | 0 | 0 | OR
661 | 81 | 057201 | Test and Balancing (CIP) | 207635 | 152518.55 | 55116.45 | 0 | OR
661 | 81 | 058101 | Test and Balancing (CIP) | 134429 | 92487.15 | 41941.85 | 0 | OR
661 | 81 | 059101 | Test and Balancing (CIP) | 84800 | 55770 | 28730 | 300 | OR
661 | 81 | 060101 | Test and Balancing (CIP) | 117673 | 117673 | 0 | 0 | OR
661 | 81 | 061201 | Test and Balancing (CIP) | 68015 | 68015 | 0 | 0 | OR
661 | 81 | 070301 | Test and Balancing (CIP) | 25036 | 0 | 5750 | 19286 | OR
661 | 81 | 081204 | Test and Balancing (CIP) | 17500 | 0 | 0 | 17500 | OR
661 | 81 | 125131 | Test and Balancing (CIP) | 40205 | 0 | 0 | 40205 | OR
661 | 81 | 147101 | Test and Balancing (CIP) | 7534 | 7534 | 0 | 0 | OR
661 | 81 | 160131 | Test and Balancing (CIP) | 67475 | 67475 | 0 | 0 | OR
661 | 81 | 184131 | Test and Balancing (CIP) | 40205 | 0 | 0 | 40205 | OR
661 | 81 | 194101 | Test and Balancing (CIP) | 22082 | 0 | 0 | 22082 | OR
661 | 81 | 256131 | Test and Balancing (CIP) | 124025 | 0 | 124025 | 0 | OR
661 | 81 | 000000 | City of Fort Worth Trust Account for Permit Fees (CIP) | 0 | 0 | 0 | 0 | ISD
661 | 81 | 000000 | City of Fort Worth Trust Account for Permit Fees (CIP) | 300000 | 0 | 152339.67 | 147660.33 | ISD
661 | 81 | 021111 | Zoning Planing and Permitting Services (CIP) | 24845 | 0 | 24845 | 0 | OR
661 | 81 | 044201 | Zoning Planing and Permitting Services (CIP) | 2736 | 0 | 0 | 2736 | OR
661 | 81 | 044202 | Zoning Planing and Permitting Services (CIP) | 22825 | 22825 | 0 | 0 | OR
661 | 81 | 045101 | Zoning Planing and Permitting Services (CIP) | 1368 | 315 | 1053 | 0 | OR
661 | 81 | 048102 | Zoning Planing and Permitting Services (CIP) | 0 | 0 | 0 | 0 | OR
661 | 81 | 050102 | Zoning Planing and Permitting Services (CIP) | 73661 | 0 | 0 | 73661 | OR
661 | 81 | 053301 | Zoning Planing and Permitting Services (CIP) | 3192 | 3192 | 0 | 0 | OR
661 | 81 | 055202 | Zoning Planing and Permitting Services (CIP) | 34638 | 0 | 0 | 34638 | OR
661 | 81 | 057201 | Zoning Planing and Permitting Services (CIP) | 9185 | 0 | 9185 | 0 | OR
661 | 81 | 125131 | Zoning Planing and Permitting Services (CIP) | 17280 | 17280 | 0 | 0 | OR
661 | 81 | 184131 | Zoning Planing and Permitting Services (CIP) | 15038 | 15037.5 | 0 | 0.5 | OR
661 | 81 | 256131 | Furniture, Fixture, & Equipment (CIP) | 17214 | 0 | 17214 | 0 | OR
661 | 81 | 000000 | Building & Land Acquisition (CIP) | 523524 | 0 | 523524 | 0 | ISD
661 | 81 | 256131 | Basic | 230413.37 | 0 | 222813.37 | 7600 | OR